## Parsing_&_Structure
#	Task	Priority	Effort/Difficulty	Status	Notes
1	Mutable variables are defined with 'var {variable} (: type) = expr'	Medium	Low	100%
2	Immutable variables are defined with 'val {value} (:type) = expr'	Medium	Low	100%
3	Public modifier not allowed for mutable fields	Medium	Low	100%
4	Set required default access levels: Field = private, method = public, class/record = internal, trait = public	Medium	Low	75%	Not implemented for un-implemented types (record, mixin, trait)
5	Tuple assignment at class level (e.g. 'val (a, b) = tuple')	Medium	Low	0%
6	Disallow empty parameter methods (must be readonly property)	Low	Low	0%	Still debating whether this useful, or if it should even happen. Lots of core CLR methods use methods with no parameters
7	Change property declaration to Fireball spec	Medium	Moderate	0%	See Language notes / specification for details
8	Implement default constructors for classes	Medium	Low	100%	All parameters get implemented as readonly private fields
9	Implement default constructors for records	Low	Moderate	0%	All parameters get implemented as public read/write properties (Pascal cased)
10	Reintroduce the 'new' keyword for creating new instances	Medium	Moderate	0%
11	Default constructor propertly handles default literal values	Low	Low	100%
12	Implement access modifiers on default constructors	Medium	Moderate	0%
13	Remove null value	Medium	Low	75%	This will potentially break other parts of the compiler
14	Implement newline handling / parser specification for newlines	High	High	100%	Latest test seems pretty crazy, and works just fine, so I'm marking this done for now
15	Change match '|' operator and exception '|' operator to new keyword "case"	Medium	Low	50%
16	Extend 'using' statements to be allowed anywhere	Medium	High	95%	Probably will have to setup some sort of alias (compiler generated), which gets scoped / to where the 'using' statement is specified. There might be a better way but this is my / current plan.
17	Implement generic 'environment sensitive' keywords	Medium	High	0%	Like 'as' in match statement, 'get'/'set' in property definition, 'add'/'remove' in event, etc.
18	Remove numeric postfix operators '++' and '--'	Low	Low	0%
19	Change '++' macro to be useful for any ICollection / ICollection[T]	Low	Low	0%	Depends on task #18
20	Change tuple type declaration to be parathesis style, not union style (i.e. using '(Type1, Type2, …)' instead of 'Type1 * Type2, …'	Low	Low	0%
21	Rename all namespaces to 'Fireball.Compiler'	Medium	High	0%	Will probably break lots of shit. Might require multiple revs / other tasks
22	Update to Fireball Keywords	Medium	Moderate	45%	Several keywords have been implemented
23	VarParms (vardef) should be triggered by ellipsis instead of the keyword "params"	Low	Low
	Change 'where' clause for type bounds to be integrated into generic type brackets […]	Low	Low	100%

## Types_&_Internals
Task	Priority	Effort/Difficulty	Status	Notes
Implement Record type	Medium	High	50%	Needs fixing
Implement Traits	High	High	0%	See language specification for more details
Implement Mixins	Medium	Extensive	0%
Handle non-literal default value arguments	Low	Moderate	75%	Currently implemented using parameter subsets, needs to change to callsite tracking of named parameters and private static readonly fields for default values
Type inference for fields defined at class level initialized to literal values	Low	Low	100%
Type inference for fields defined at class level initialized to non-literal values	Medium	Low	100%
Inject all non-member code specified at class level into private ctor	High	High	0%	This ctor should have a special attribute that indicates it should be called by / all constructors that don't call an overloaded constructor.
Remove explicit enumerations and change variant type inheriting from numeric type to emit enumeration	Low	Moderate	0%
Implement companion modules	Medium	Moderate	0%
Implement 'if' ('else if' / 'else') as a compiler level feature (not a macro)	Low	Moderate	0%
Remove useless, unplanned, not-supported macros from Macros library	Medium	High	0%
Allow modules to implement traits	Low	Moderate	0%	Using some compiler trick to generate a private class which is exposed via a public property with the same name as the implemented interface.
Add resolve / resolved for compile time parameter / field value resolution	Medium	Moderate	65%
Add lower type bounds to type system	Medium	Low	85%	Still need to implement the metadata (attribute) and have the compiler pick it up on assembly load from referenced assemblies